## Sheet1
[5 empty] | HTML |  |  |  | Implementation
Section |  | Sub Section | Liferay Component | Remarks | Effort (Hours) | Start Date | Expected End Date | Actual End Date | Effort (Hours) | Unit Testing (Hours) | QA Deployment (Hours) | Start Date | End Date
Footer Links - Disclaimer (single page) | Single Page | Marquee | Web Content | [5 empty] | 0.5 | 1 | 1
|  | Home Banner , Breadcrumbs | Web Content | [5 empty] | 0.5 | 1 | 1
|  | Secondary Navigation | Global Web Content | [5 empty] | 0.5 | 1 | 1
|  | Overview | Structure , Web Content | HTML is required |  |  |  |  | 1 | 1 | 1
|  | Disclaimer of Warranties and Liability | Web Content | [5 empty] | 1 | 1 | 1
|  | Right of Access | Web Content | [5 empty] | 1 | 1 | 1
|  | Links from this Website to other websites | Web Content | [5 empty] | 1 | 1 | 1
|  | Links to this Website From other websites | Web Content | [5 empty] | 1 | 1 | 1
|  | Install RBI aaplication - Footer | Global Web Content | [5 empty] | 0.5 | 1 | 1
Function wise Sites - Currency Management | Overview | Marquee | Web Content
|  | Home Banner , Breadcrumbs | Web Content
|  | Secondary Navigation | Global Web Content
|  | Overview Content | Structure , Web Content
|  | Overview Accordion | Web Content
|  | Legal Framework | Web Content
|  | RbiSocialMediaUtility | Global Web Content
|  | Install RBI aaplication - Footer | Global Web Content
| Notification | Marquee | Web Content
|  | Home Banner , Breadcrumbs | Web Content
RBINotificationSearchFilter
Search Results - List View
Search Results - Card View
Notification Detailed Page
|  | RbiSocialMediaUtility | Global Web Content
|  | Install RBI aaplication - Footer | Global Web Content
| Press Release | Marquee | Web Content
|  | Home Banner , Breadcrumbs | Web Content
RBINotificationSearchFilter
Search Results - List View
Search Results - Card View
Press Release Detailed Page
|  | RbiSocialMediaUtility | Global Web Content
|  | Install RBI aaplication - Footer | Global Web Content
| Speeches | Marquee | Web Content
|  | Home Banner , Breadcrumbs | Web Content
RBISpeechesInterviewSearchFilters
Search Results - List View
Search Results - Card View
Speeches Detailed Page
|  | RbiSocialMediaUtility | Global Web Content
|  | Install RBI aaplication - Footer | Global Web Content
| Interviews | Marquee | Web Content
|  | Home Banner , Breadcrumbs | Web Content
InterviewsSearchBar
Search Results - List View
Search Results - Card View
Interviews Detailed Page
|  | RbiSocialMediaUtility | Global Web Content
|  | Install RBI aaplication - Footer | Global Web Content
| FAQs |  |  | Unable to load page -> Loading…
| History / Records |  |  | Financial Market -> Withdrawn Circulars
| Other Links | Marquee | Web Content
|  | Home Banner , Breadcrumbs | Web Content
|  | Other Links | Web Content
|  | RbiSocialMediaUtility | Global Web Content
|  | Install RBI aaplication - Footer | Global Web Content